## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Introduction to AI Compliance Checker and LLms, compliance in GDPR and HIPAA jurisdiction | MUST HAVE | No Dependency | SUSNATA JANA | 3- Completed
S1 | S1 | US-001 | Automatic identification of the Key Clauses in Contracts | MUST HAVE | No Dependency | SUSNATA JANA | 3- Completed
S2 | S2 | US-001 | Continuously monitor legal databases for changes | MUST HAVE | No Dependency | SUSNATA JANA | 3- Completed
S2 | S2 | US-001 | Suggest modifications to contracts based on detected risks | SHOULD HAVE | No Dependency | SUSNATA JANA | 3- Completed
S3 | S3 | US-001 | Analyzed risks for the missing Clauses | MUST HAVE | No Dependency | SUSNATA JANA | 3- Completed
S3 | S3 | US-001 | Contract Modification & Recommendations | MUST HAVE | No Dependency | SUSNATA JANA | 2- In Progress
S3 | S3 | US-001 | Automatically updated risky/missing contract sections. | MUST HAVE | No Dependency | SUSNATA JANA | 3- Completed
S4 | S4 | US-001 | Integrated with Google Sheets API for contract storage. | MUST HAVE | Google Sheets API | SUSNATA JANA | 3- Completed
S4 | S4 | US-001 | Final Testing, Deployment, Functional testing across all modules (Clause, Risk, Updates, Notifications) | MUST HAVE | Github,VS Code | SUSNATA JANA | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 40 | 19 | 12 | 8 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | 1 | Introduction to AI Compliance Checker and LLms, compliance in GDPR and HIPAA jurisdiction | 2025-09-19 | 2025-09-23 | SUSNATA JANA | Others | Completed | 4 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 2 | Install Scraping Tools & Project Folder Structure, Research GDPR/HIPAA regulatory frameworks | 2025-09-24 | 2025-09-27 | SUSNATA JANA | Research | Completed | 4 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 3 | Collect sample contracts from dataset sources, Preprocess & clean contract documents | 2025-09-30 | 2025-10-04 | SUSNATA JANA | Build | Completed | 6 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 4 | Integrate OpenAI GPT / LLaMA for clause extraction, Build prompt templates for clause classification | 2025-10-07 | 2025-10-11 | SUSNATA JANA | Coding | Completed | 6 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 5 | Implement LLM-based risk scoring model, Integrate clause engine + risk engine | 2025-10-14 | 2025-10-18 | SUSNATA JANA | Coding | Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 6 | Regulatory Update Tracker,Connect update tracker with risk engine | 2025-10-21 | 2025-10-25 | SUSNATA JANA | Coding | Completed | 5 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 7 | Contract Modification Module, Integrate recommendations into workflow | 2025-10-28 | 2025-11-01 | SUSNATA JANA | integration | Completed | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 8 | Multi-Platform Integrations, Integrate with Google Sheets API, Assignment 3 | 2025-11-04 | 2025-11-09 | SUSNATA JANA | Build, Integrate | Completed | 4 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 9 | Fix bugs, optimise prompts & accuracy, prepare documentation, push into GitHub | 2025-11-11 | 2025-11-14 | SUSNATA JANA | Test, Push | Completed | 5 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 5 | Unclear regulatory requirements (GDPR/HIPAA) for mapping into system. | Conducted detailed research and summarized key compliance articles for reference.
Sprint 2 | Day 7 | Inconsistent formatting in collected contract documents caused preprocessing delays. | Applied automatic text cleaning rules and standardized formatting via preprocessing script.
Sprint 3 | Day 12 | Clause extraction accuracy low during initial GPT/LLaMA tests. | Improved prompt engineering and added more contract samples for better training context.
Sprint 4 | Day 16 | Mapping risk rules to regulations lacked clarity due to overlapping policies. | Cross-checked GDPR/HIPAA rules and created a consolidated regulation-to-clause mapping sheet.
Sprint 5 | Day 20 | Legal update APIs returning incomplete/duplicate regulatory updates. | Switched to alternative sources, added deduplication logic, and improved API parsing.
Sprint 6 | Day 24 | LLM-generated amendment suggestions were too generic. | Added contextual prompts with clause history and contract metadata to improve specificity.
Sprint 7 | Day 28 | Google Sheets API authentication issues caused integration delays. | Regenerated credentials, tested OAuth flow, and successfully linked with Google API.
Sprint 8 | Day 34 | Minor bugs during final system integration (risk scores not updating). | Fixed logic issues, retested modules, and validated end-to-end workflows.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 2 | 2024-09-30 | 2024-10-04 | SUSNATA JANA | Following a structured plan for data cleaning and preprocessing | Ignoring document formatting inconsistencies | Staying consistent with daily preprocessing tasks | Standardized all contract documents using unified preprocessing rules
2 | Sprint 3 | 2024-10-07 | 2024-10-11 | SUSNATA JANA | Experimenting with multiple prompt styles for clause extraction | Relying on a single model output without verification | Testing clause extraction on diverse contract samples | Improved extraction accuracy by refining prompts and testing across multiple documents
3 | Sprint 4 | 2024-10-14 | 2024-10-18 | SUSNATA JANA | Mapping regulations against specific contract clauses more precisely | Interpreting regulations without cross-checking sources | Maintaining documentation of regulatory rules | Created a consolidated GDPR & HIPAA clause-mapping sheet
4 | Sprint 5 | 2024-10-21 | 2024-10-25 | SUSNATA JANA | Validating legal update sources before integrating APIs | Using unreliable or incomplete legal API endpoints | Continuously testing data extraction workflow | Implemented new legal sources and added deduplication logic
5 | Sprint 6 | 2024-10-28 | 2024-11-01 | SUSNATA JANA | Testing LLM-generated clause recommendations manually for quality | Accepting generic clause suggestions without refinement | Applying improved contextual prompts | Produced more accurate and contract-specific amendment recommendations
6 | Sprint 7 | 2024-11-04 | 2024-11-08 | SUSNATA JANA | Running integration tests early when connecting Google Sheets | Delaying API integration until later stages | Maintaining smooth communication implementation | Fixed API credential issues and connected all platforms successfully
7 | Sprint 8 | 2024-11-11 | 2024-11-14 | SUSNATA JANA | Finalizing testing | Performing full system regression testing | Performing full system regression testing | And Push the Project to GitHub